## Instructions
ITC327W Phase 2 Project Progress Tracker
Use this workbook during Phase 2: System Architecture and Design. Update it throughout the phase and submit the same workbook with Assessment 2.
Sheet | Purpose | What must be kept current
Project Overview | Group details and automatic progress summary | Group information, GitHub link and current Phase 2 progress
Design Progress | Track each design artefact and supporting work | Architecture, UML, ERD, mobile/web interfaces, SRS and project-management tasks
Individual Contributions | Record work personally completed by each student | Activity, responsibility, work completed and evidence
Design Source Links | Record editable source links/files for submitted designs | Architecture, UML, ERD, mobile and web design sources
Challenges & Actions | Record design/project challenges and corrective action | Problem, effect, action, owner, target date and status
Phase Summary | Summarise what was achieved and what remains | Phase status, completed work, gaps and next priorities
Group Reflection | One shared group reflection for Phase 2 | Participation, collaboration, challenges, learning and improvements
Important
Do not create a separate tracker for each activity. This Phase 2 workbook is updated as the group progresses. Evidence may include GitHub commits, screenshots, document sections, editable design links/files and other appropriate project evidence. Do not include passwords, API keys or confidential stakeholder information.

## Project Overview
Phase 2 Project Overview
Group | J | Phase 2 Progress Summary
Project Title | Easy Rentals Student Accommdation | Total tracked items | 12
Stakeholder / Organisation | Easy Rentals | Completed | 12
Group Leader | Sthembiso Thabethe | In Progress | 0
Number of Group Members | 8 | Blocked | 0
GitHub Repository Link | https://github.com/Theo-debugg/Easy-Rentals-Accommodation-management-system-.git | Average completion | 100%
Reporting Period | Phase 2
Overall Phase Status | Completed | Phase 2 Reminder
Phase 2 focuses on system architecture and design. Track the design artefacts, the editable source links/files, individual contributions, challenges, Microsoft Project updates and GitHub evidence. No separate stakeholder-evidence section is required in this tracker.

## Design Progress
Phase 2 Design Progress
Task ID | Design / Project Item | Description / Expected Output | Responsible Student(s) | Planned Date | Actual Completion Date | Status | % Complete | Evidence / Link | Notes / Action Required
P2-01 | System Architecture | Overall architecture showing Flutter, ASP.NET and shared Supabase backend | Everyone | 9/17/26 | Completed | Completed | 100% | https://lucid.app/lucidchart/d8c7306c-da9c-4b2e-a34d-2d6b52defdb1/edit?viewport_loc=-556%2C-62%2C3248%2C1618%2C0_0&invitationId=inv_118af968-481f-4907-9049-6fcb8e7fdecd
P2-02 | Use Case Diagram | Actors, use cases, system boundary and appropriate UML relationships | Everyone |  | Completed | Completed | 100% | https://lucid.app/lucidchart/2b063380-1ef2-478a-aeb2-bfa37c88595b/edit?viewport_loc=-951%2C-915%2C2637%2C1818%2C0_0&invitationId=inv_a872a4e7-3bd8-474d-a1f9-dabc69af82b7
P2-03 | Sequence Diagram 1 | Important Flutter process | Everyone |  | Completed | Completed | 100% | https://lucid.app/lucidchart/8de32e4d-911c-431b-a35b-127f77eed3db/edit?invitationId=inv_8a53e061-7771-4c2f-b72c-a4b1d28faedc&page=0_0
P2-04 | Sequence Diagram 2 | Important ASP.NET process | Everyone |  | Completed | Completed | 100% | https://lucid.app/lucidchart/42326f7e-e6e0-44f5-96fe-e8685c29f9b8/edit?viewport_loc=-3198%2C-4201%2C7949%2C3960%2C0_0&invitationId=inv_bc6f1276-4c17-4035-a3e4-372034c6bb37
P2-05 | ERD | Entities, attributes, PKs, FKs, relationships and cardinality | Toka Malachamela, Tshiamo Goitsemodimo |  | Completed | Completed | 100% | https://lucid.app/lucidchart/76039561-d095-45b5-856f-46c3432533c2/edit?viewport_loc=-491%2C-468%2C2933%2C1542%2C0_0&invitationId=inv_123df1f3-67c9-4362-b0fd-3d8b4863f2c5
P2-06 | Flutter Interface Designs | Main mobile screens and navigation | Tshiamo Goitsemodimo, Onalenna Shea, Tshepang Mahase, Palesa Lesekele |  | Completed | Completed | 100% | https://www.figma.com/design/f1h48hYRyC20CkUCM3jJfT/Untitled?node-id=1-2&t=eG3l927EvEUnjZaK-1
P2-07 | ASP.NET Interface Designs | Main web pages and navigation | Thierry Sithole, Sthembiso Thabethe, Toka Malachamela, Thapelo Magwai |  | Completed | Completed | 100% | https://www.figma.com/design/4QkvwEdkyLsApZxUQzr2T2/Untitled?node-id=0-1&t=zz3fHoyhFXS0Nb5u-1
P2-08 | Design Alignment | Requirements linked across UML, ERD and interfaces | Tshiamo Goitsemodimo, Onalenna Shea, Tshepang Mahase, Palesa Lesekele, Thierry Sithole, Sthembiso Thabethe, Toka Malachamela, Thapelo Magwai |  | Completed | Completed | 100%
P2-09 | Updated SRS | Phase 2 architecture and design section inserted in existing SRS | Sthembiso Thabethe |  | Completed | Completed | 100%
P2-10 | Microsoft Project | Schedule updated to reflect design progress and upcoming development | Onalenna Shea |  | Completed | Completed | 100%
P2-11 | GitHub | Current design documentation and repository organisation | Thierry Sithole |  | Completed | Completed | 100% | https://github.com/Theo-debugg/Easy-Rentals-Accommodation-management-system-.git
P2-12 | Phase 2 Presentation | Presentation and defence preparation | Everyone |  | Completed | Completed | 100%

## Individual Contributions
Phase 2 Individual Contributions
Student Name | Student Number | Activity / Artefact | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Quality / Review Notes | Contribution Status
Onalenna Shea | 224076426 |  | Gantt Chart | Gantt Chart | 2026-10-08 | 5 min |  | Yes | 2026-10-12 |  | Completed
Sthembiso Thabethe | 221030472 |  | Edited the SRS Document | Edited the SRS Document | 2026-10-12 | 7 hours |  | Yes | 2026-10-13 |  | Completed
Tshepang Mahase | 223051300 |  | Use Case Diagram | Use Case Diagram | 2026-10-12 | 6 hours | https://lucid.app/lucidchart/2b063380-1ef2-478a-aeb2-bfa37c88595b/edit?viewport_loc=-951%2C-915%2C2637%2C1818%2C0_0&invitationId=inv_a872a4e7-3bd8-474d-a1f9-dabc69af82b7 | Yes | 2026-10-14 |  | Completed
Thapelo Magwai | 223035662 |  | Design System Architecture | Design System Architecture | 2026-10-08 | 1 hours | https://lucid.app/lucidchart/d8c7306c-da9c-4b2e-a34d-2d6b52defdb1/edit?viewport_loc=-556%2C-62%2C3248%2C1618%2C0_0&invitationId=inv_118af968-481f-4907-9049-6fcb8e7fdecd | Yes | 2026-10-15 |  | Completed
Toka Malachamela | 221000945 |  | ERD Diagram | ERD Diagram | 2026-10-08 | 9 hours | https://lucid.app/lucidchart/76039561-d095-45b5-856f-46c3432533c2/edit?viewport_loc=-491%2C-468%2C2933%2C1542%2C0_0&invitationId=inv_123df1f3-67c9-4362-b0fd-3d8b4863f2c5 | Yes | 2026-10-16 |  | Completed
Tshiamo Goitsemodimo | 223059551 |  | ERD Diagram | ERD Diagram | 2026-10-08 | 9 hours | https://lucid.app/lucidchart/76039561-d095-45b5-856f-46c3432533c2/edit?viewport_loc=-491%2C-468%2C2933%2C1542%2C0_0&invitationId=inv_123df1f3-67c9-4362-b0fd-3d8b4863f2c5 | Yes | 2026-10-17 |  | Completed
Palesa Lesekele | 223035639 |  | Sequence Diagram | Sequence Diagram | 2026-10-08 | 12 hours | https://lucid.app/lucidchart/8de32e4d-911c-431b-a35b-127f77eed3db/edit?invitationId=inv_8a53e061-7771-4c2f-b72c-a4b1d28faedc&page=0_0 | Yes | 2026-10-18 |  | Completed
Thierry Sithole | 224061529 |  | Updated the Github Repository | Updated the Github Repository | 2026-10-11 | 30 min | https://github.com/Theo-debugg/Easy-Rentals-Accommodation-management-system-.git | Yes | 2026-10-19 |  | Completed
All |  |  | Wireframes | Wireframes | 2026-10-10 | 48 hours | https://www.figma.com/design/f1h48hYRyC20CkUCM3jJfT/Untitled?node-id=1-2&t=eG3l927EvEUnjZaK-1 | Yes | 2026-10-20 |  | Completed
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started

## Design Source Links
Phase 2 Original Design Source Links / Files
Design Artefact | Tool Used | Editable Link / File Name | Accessible to Lecturer? | Last Updated | Responsible Student | Included in SRS? | Notes
System Architecture | Lucid Software | https://lucid.app/lucidchart/d8c7306c-da9c-4b2e-a34d-2d6b52defdb1/edit?viewport_loc=-556%2C-62%2C3248%2C1618%2C0_0&invitationId=inv_118af968-481f-4907-9049-6fcb8e7fdecd | Yes | 2026-08-10 | Everyone | Yes
Use Case Diagram | Lucid Software | https://lucid.app/lucidchart/2b063380-1ef2-478a-aeb2-bfa37c88595b/edit?viewport_loc=-951%2C-915%2C2637%2C1818%2C0_0&invitationId=inv_a872a4e7-3bd8-474d-a1f9-dabc69af82b7 | Yes | 2026-08-10 | Everyone | Yes
Sequence Diagram 1 | Lucid Software | https://lucid.app/lucidchart/8de32e4d-911c-431b-a35b-127f77eed3db/edit?invitationId=inv_8a53e061-7771-4c2f-b72c-a4b1d28faedc&page=0_0 | Yes | 2026-08-10 | Everyone | Yes
Sequence Diagram 2 | Lucid Software | https://lucid.app/lucidchart/42326f7e-e6e0-44f5-96fe-e8685c29f9b8/edit?viewport_loc=-3198%2C-4201%2C7949%2C3960%2C0_0&invitationId=inv_bc6f1276-4c17-4035-a3e4-372034c6bb37 | Yes | 2026-08-10 | Everyone | Yes
ERD | Lucid Software | https://lucid.app/lucidchart/76039561-d095-45b5-856f-46c3432533c2/edit?viewport_loc=-491%2C-468%2C2933%2C1542%2C0_0&invitationId=inv_123df1f3-67c9-4362-b0fd-3d8b4863f2c5 | Yes | 2026-08-10 | Toka Malachamela, Tshiamo Goitsemodimo | Yes
Flutter Interface Designs | Figma | https://www.figma.com/design/f1h48hYRyC20CkUCM3jJfT/Untitled?node-id=1-2&t=eG3l927EvEUnjZaK-1 | Yes | 2026-10-10 | Tshiamo Goitsemodimo, Onalenna Shea, Tshepang Mahase, Palesa Lesekele | Yes
ASP.NET Interface Designs | Figma | https://www.figma.com/design/4QkvwEdkyLsApZxUQzr2T2/Untitled?node-id=0-1&t=zz3fHoyhFXS0Nb5u-1 | Yes | 2026-10-10 | Thierry Sithole, Sthembiso Thabethe, Toka Malachamela, Thapelo Magwai | Yes
Navigation Flow | Figma(flutter) | https://www.figma.com/proto/f1h48hYRyC20CkUCM3jJfT/Flutter-mobile-app?node-id=1-3&starting-point-node-id=1%3A3&t=NsZvGtre3OLMIQpY-1 | Yes | 2026-10-10 | Tshiamo Goitsemodimo, Onalenna Shea, Tshepang Mahase, Palesa Lesekele,Thierry Sithole, Sthembiso Thabethe, Toka Malachamela, Thapelo Magwai | Yes
Navigation Flow | Figma(asp.net) | https://www.figma.com/proto/f1h48hYRyC20CkUCM3jJfT/Flutter-mobile-app?node-id=1-3&starting-point-node-id=1%3A3&t=NsZvGtre3OLMIQpY-1 https://www.figma.com/proto/4QkvwEdkyLsApZxUQzr2T2/ASP.NET-WIREFRAMES?node-id=8-20&starting-point-node-id=6%3A31&t=RaruzWRoQjQAslUZ-1 | Yes | 2026-10-10 | Tshiamo Goitsemodimo, Onalenna Shea, Tshepang Mahase, Palesa Lesekele,Thierry Sithole, Sthembiso Thabethe, Toka Malachamela, Thapelo Magwai | Yes

## Challenges & Actions
Phase 2 Challenges and Corrective Actions
Date Identified | Challenge | Effect on Progress / Design | Corrective Action | Responsible Student | Target Date | Status | Resolved Date | Notes
2026-09-25 | Constructing the ERD Diagram | Delayed progress by a day | Went through previous learning material and provided Youtube videos to get an understanding of the work required | Tshiamo Goitsemodimo, Toka Malachamela | 2026-10-11 | Completed | 2026-10-10 | Always go through previous learning material to refresh ourselves
2026-10-09 | Meeting time with the stakeholder | Delayed the Progress of Phase 2 | Migrated to whatsapp messages | Thierry Sithole | 2026-10-11 | Completed | 2026-10-11 | Present any requests to the stakeholder on time.
2026-10-05 | Microsoft Teams meeting setup | Delayed the Progress of Phase 2 | Asked another group member to setup the meeting | Onalenna Shea, Sthembiso Thabethe | 2026-10-05 | Completed | 2026-10-05 | Setup the meeting link on time, to avoid any delays
2026-10-01 | Constructing the UML Use Case Diagram | Created Uncertainty when it comes to Wireframes | Consulted different lectures to get a clear picture of what we should do | Toka Malachamela, Onalenna Shea, Sthembiso Thabethe | 2026-10-12 | Completed | 2026-10-12 | Extend the functionality on some use cases.
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Phase Summary
Phase 2 Progress Summary
Reporting Period | 09/14/2026 - 10/12/2026 | Phase 2 Completion Checklist | Complete?
Overall Phase Status | Completed | Architecture complete | Yes
What was completed during Phase 2? | System Architecture, Use case diagram, Sequence diagrams, ERD, Wireframes, Navigation flow, updating github repository, update SRS document, updating Gantt Chart | Use Case Diagram complete | Yes
What remains incomplete? | Nothing remain incomplete | Two Sequence Diagrams complete | Yes
Why is it incomplete? | N/A | ERD complete | Yes
Which contributions were particularly important? | Our joint review sessions, which found and fixed gaps between the screens, ERD and use cases. | Flutter interfaces complete | Yes
Were there participation concerns? | There were no participation concerns | ASP.NET interfaces complete | Yes
What will the group improve in Phase 3? | Agree on names before coding, test integration early, and commit to GitHub regularly. | Editable source links/files recorded | Yes
Main priority for Phase 3 | Build the Supabase database and prioritize commiting to github. | SRS updated | Yes
|  | Microsoft Project updated | Yes
|  | GitHub current | Yes
|  | Individual contributions recorded | Yes
|  | Challenges/actions updated | Yes
|  | Group reflection completed | Yes

## Group Reflection
Phase 2 Group Reflection
1. What did the group complete successfully during Phase 2?
System Architecture, Use case diagram, Sequence diagrams, ERD, Wireframes, Navigation flow, updating github repository, update SRS document, updating Gantt Chart
2. Which architecture or design activities were the most challenging?
ERD, Sequence diagram, Use case diagram
3. How did the group ensure that Flutter, ASP.NET and Supabase were designed as one integrated system?
We designed both applications around one shared Supabase database instead of separate data stores. The sequence diagrams show that a viewing request created in Flutter is stored in Supabase and then retrieved and approved through ASP.NET, and the student sees the updated status back in Flutter. We then checked every screen against the ERD, so each piece of information captured in one app could be stored and read by the other. Where it couldn't, we fixed it, for example by adding Room_ID to Viewing Request.
4. How was work divided among group members, and was participation balanced?
Since the phase consisted of one unit. The activities were then distributed among members to share the workload and allow different tasks to progress simultaneously. We then reviewed, and rectified the mistakes as a group. Participation was balanced as each group member did their part as the work was evenly ditributed.
5. What did the group learn from developing the UML, ERD and interface designs?
We learned that each design must be checked against the others, not just completed on its own. Designing the screens exposed gaps the diagrams had missed, such as a Cancel Appointment use case with no cancel button, a student with no way to log out, and a room-management use case with no delete option. We also learned to use «include», «extend» and alt boxes only where they reflect real behaviour in our system, and to keep terms the same across every artefact.
6. What will the group do differently during development in Phase 3?
We will agree on one set of names for screens, tables and statuses before writing any code, and set up the Supabase tables from the final ERD first so both applications build on the same structure. We will test the Flutter-to-ASP.NET connection early, for example by submitting a request in Flutter and confirming it appears in ASP.NET, rather than waiting until the end.We will also commit work to GitHub regularly with clear messages, record changes in a change log, and check in with the stakeholder more often so feedback reaches us before development is finished.